## Task Tracker
ID | Module | Task | Owner | Day | Status | Priority | GitHub
T01 | Setup | Finalize modules + architecture diagram | Both | 1 | Done | MUST | main
T02 | Setup | Repo + folder structure + README skeleton | Both | 1 | Done | MUST | main
T03 | Setup | Define ModuleResult / Finding contract (utils/common.py) | Me | 1 | Done | MUST | main
T04 | Setup | Define finding IDs, chain rules + ATT&CK mapping, risk formula | Me | 1 | Done | MUST | main
T05 | Setup | Define DB schema and UI page list | Teammate | 1 | Done | MUST | main
T06 | Password | Length / class / entropy checks | Me | 2 | Done | MUST | password-module
T07 | Password | Common-password list (SecLists 10k) + dictionary + leetspeak | Me | 2 | Done | MUST | password-module
T08 | Password | Sequence / repeat / name+digits / year patterns, reuse flag | Me | 2 | Done | MUST | password-module
T09 | Device | Questionnaire, weights, 'Not sure' = half risk | Teammate | 2 | Done | MUST | dashboard
T10 | URL | URL parsing, registered domain, feature extraction | Me | 3 | Done | MUST | url-module
T11 | URL | HTTPS / IP / TLD / @ / shortener / punycode / homograph rules | Me | 3 | Done | MUST | url-module
T12 | ML-URL | URL dataset collection + preprocessing | Teammate | 3 | Done | MUST | url-module
T13 | ML-URL | Train RF + XGBoost, evaluate, serialize | Teammate | 4 | Done | MUST | url-module
T14 | URL | Rule + ML fusion, SHAP, disagreement flag | Me | 4 | Done | SHOULD | url-module
T15 | Email | Header analysis (Reply-To, spoofing, SPF/DKIM/DMARC) | Me | 5 | Done | MUST | email-module
T16 | Email | Content rules + India-localized lexicon (C5) | Me | 5 | Done | NICE | email-module
T17 | ML-Email | Email dataset + TF-IDF + LR / RF training | Teammate | 5 | Done | MUST | email-module
T18 | Email | Header + Content + URL + ML -> Email risk; test samples | Both | 6 | Done | MUST | email-module
T19 | Permissions | Permission -> severity table, category baseline, manifest parser | Teammate | 7 | Done | MUST | dashboard
T20 | Risk | Risk engine: renormalised weights, coverage, baseline_score | Me | 8 | Done | MUST | risk-engine
T21 | Correlation | Threat Correlation Engine: chains, escalation, critical floor | Me | 8 | Done | MUST | correlation-engine
T22 | Risk | Score breakdown (points lost) + reconciliation test | Me | 8 | Done | SHOULD | risk-engine
T23 | Recommendations | Finding -> action -> priority mapping | Me | 9 | Done | MUST | risk-engine
T24 | What-If | Counterfactual simulator + ranking by gain/effort | Me | 9 | Done | SHOULD | risk-engine
T25 | Dashboard | Streamlit pages: scanner, dashboard, what-if, history, report, about | Teammate | 10 | Done | MUST | dashboard
T26 | Dashboard | Attack-chain panel, waterfall, UNCERTAIN badges, what-if toggles | Teammate | 10 | Done | SHOULD | dashboard
T27 | Database | SQLite persistence (IDs and scores only) | Teammate | 11 | Done | MUST | dashboard
T28 | History | History page + trend chart + improvement delta | Teammate | 11 | Done | SHOULD | dashboard
T29 | Report | HTML report + PDF export | Teammate | 11 | Done | SHOULD | dashboard
T30 | Integration | End-to-end pipeline freeze (no new features) | Both | 12 | Done | MUST | main
T31 | Testing | pytest unit tests + module test suites | Both | 13 | Done | MUST | main
T32 | Evaluation | Scenario study (C1) | Me | 13 | Done | MUST | main
T33 | Evaluation | Adversarial URL robustness test | Teammate | 13 | Done | NICE | main
T34 | Evaluation | Rule-ML disagreement statistics + India test set | Me | 13 | Done | NICE | main
T35 | Final | Bug fixes, README, screenshots, limitations, future work | Both | 14 | Testing | MUST | main
T36 | Final | Demo rehearsal, PPT, viva prep (VIVA_PREP.md) | Both | 14 | In Progress | MUST | main

## Test Cases
Test ID | Module | Input (sanitized) | Expected | Actual | Status | Issue | Fixed?
PW01 | password | [6 chars] top common password | CRITICAL | CRITICAL (0) | Pass
PW02 | password | [8 chars] common dictionary | CRITICAL | CRITICAL (12) | Pass
PW03 | password | [8 chars] leetspeak common | CRITICAL | CRITICAL (25) | Pass
PW04 | password | [9 chars] keyboard + digits | CRITICAL | CRITICAL (6) | Pass
PW05 | password | [8 chars] common phrase | CRITICAL | CRITICAL (12) | Pass
PW06 | password | [12 chars] name + digits (spec example) | HIGH | HIGH (50) | Pass
PW07 | password | [10 chars] name + year | HIGH¦CRITICAL | HIGH (49) | Pass
PW08 | password | [11 chars] word + year | HIGH¦CRITICAL | HIGH (44) | Pass
PW09 | password | [3 chars] too short | CRITICAL | CRITICAL (32) | Pass
PW10 | password | [8 chars] repeated | CRITICAL | CRITICAL (4) | Pass
PW11 | password | [8 chars] sequence | HIGH¦CRITICAL | CRITICAL (10) | Pass
PW12 | password | [9 chars] city + 123 | HIGH¦CRITICAL | HIGH (45) | Pass
PW13 | password | [11 chars] complex but short-ish | LOW¦MODERATE | LOW (90) | Pass
PW14 | password | [28 chars] long passphrase | LOW¦MODERATE | LOW (80) | Pass
PW15 | password | [12 chars] random 12 | LOW | LOW (100) | Pass
PW16 | password | [16 chars] random 16 | LOW | LOW (100) | Pass
PW17 | password | [28 chars] diceware style | LOW | LOW (88) | Pass
PW18 | password | [20 chars] strong mixed | LOW¦MODERATE | LOW (88) | Pass
PW19 | password | [12 chars] strong but reused (reused) | MODERATE¦HIGH | MODERATE (75) | Pass
PW20 | password | [11 chars] season + year | HIGH¦CRITICAL | HIGH (49) | Pass
PW21 | password | [5 chars] default credential | CRITICAL | CRITICAL (0) | Pass
PW22 | password | [11 chars] common corporate pattern | HIGH¦CRITICAL | HIGH (45) | Pass
PW23 | password | [7 chars] keyboard row | CRITICAL | CRITICAL (0) | Pass
PW24 | password | [21 chars] passphrase | LOW | LOW (88) | Pass
PW25 | password | [10 chars] digits sequence / phone-like | CRITICAL | HIGH (47) | Fail | Reverse digit run is detected as a sequence but not in the 10k list; scores HIGH, not CRITICAL | No - documented limitation
E01 | email | [normal] Lab schedule | LOW¦MODERATE | LOW (82) | Pass
E02 | email | [normal] Lunch? | LOW¦MODERATE | LOW (84) | Pass
E03 | email | [normal] Holiday list 2027 | LOW¦MODERATE | LOW (83) | Pass
E04 | email | [normal] Viva schedule | LOW¦MODERATE | MODERATE (74) | Pass
E05 | email | [normal] photos | LOW¦MODERATE | LOW (86) | Pass
E06 | email | [promotional] Big Billion Days | LOW¦MODERATE | LOW (86) | Pass
E07 | email | [promotional] 50% off tonight | LOW¦MODERATE | HIGH (50) | Fail | ML (trained on long Western emails) gives a short promo email p~0.7; rules say LOW -> flagged UNCERTAIN | No - documented limitation
E08 | email | [promotional] New courses in machine learning | LOW¦MODERATE | LOW (84) | Pass
E09 | email | [promotional] Deals on headphones | LOW¦MODERATE | MODERATE (65) | Pass
E10 | email | [phishing] Unusual sign-in activity | HIGH¦CRITICAL | CRITICAL (2) | Pass
E11 | email | [phishing] Password expires today | HIGH¦CRITICAL | CRITICAL (8) | Pass
E12 | email | [phishing] Payment declined | HIGH¦CRITICAL | CRITICAL (3) | Pass
E13 | email | [phishing] Mailbox full | HIGH¦CRITICAL | CRITICAL (3) | Pass
E14 | email | [phishing] Your Apple ID has been locked | HIGH¦CRITICAL | CRITICAL (13) | Pass
E15 | email | [fake_sender] Refund pending | HIGH¦CRITICAL | CRITICAL (18) | Pass
E16 | email | [fake_sender] Refund for your order | HIGH¦CRITICAL | CRITICAL (3) | Pass
E17 | email | [fake_sender] Urgent request | HIGH¦CRITICAL | CRITICAL (36) | Pass
E18 | email | [fake_sender] Security alert | HIGH¦CRITICAL | CRITICAL (5) | Pass
E19 | email | [india_scam] Dear Customer, your SBI KYC update is pe... | HIGH¦CRITICAL | CRITICAL (0) | Pass
E20 | email | [india_scam] Congratulations! You have received a cas... | HIGH¦CRITICAL | CRITICAL (19) | Pass
E21 | email | [india_scam] Dear consumer your electricity power wil... | HIGH¦CRITICAL | HIGH (45) | Pass
E22 | email | [india_scam] This is Mumbai Cyber Crime police. A mon... | HIGH¦CRITICAL | CRITICAL (26) | Pass
E23 | email | [india_scam] Income Tax Dept: Your PAN is not linked ... | HIGH¦CRITICAL | HIGH (51) | Pass
E24 | email | [india_scam] KBC Lottery: Congratulations you won Rs ... | HIGH¦CRITICAL | HIGH (50) | Pass
E25 | email | [india_scam] FedEx: A parcel in your name containing ... | HIGH¦CRITICAL | MODERATE (65) | Fail | ML misses the customs scam (p~0.26); rules + embedded URL say CRITICAL; fused score MODERATE, flagged UNCERTAIN | No - documented limitation
U01 | url | wikipedia.org (legit) | LOW | LOW (86) | Pass
U02 | url | google.com (legit) | LOW | LOW (88) | Pass
U03 | url | github.com (legit) | LOW¦MODERATE | MODERATE (69) | Pass
U04 | url | amazon.in (legit brand deep link) | LOW¦MODERATE | MODERATE (74) | Pass
U05 | url | hdfcbank.com (legit bank) | LOW¦MODERATE | MODERATE (80) | Pass
U06 | url | onlinesbi.sbi (legit bank) | LOW | LOW (88) | Pass
U07 | url | python.org (legit docs) | LOW¦MODERATE | MODERATE (67) | Pass
U08 | url | irctc.co.in (legit gov) | LOW¦MODERATE | MODERATE (76) | Pass
U09 | url | google.com (legit app) | LOW¦MODERATE | LOW (80) | Pass
U10 | url | flipkart.com (legit shop) | LOW | LOW (98) | Pass
U11 | url | stackoverflow.com (legit) | LOW¦MODERATE | HIGH (40) | Fail | Lexical ML false positive on a legit deep link (non allow-listed domain); flagged UNCERTAIN | No - documented limitation
U12 | url | bbc.com (legit news) | LOW¦MODERATE | HIGH (45) | Fail | Lexical ML false positive on a legit deep link (non allow-listed domain); flagged UNCERTAIN | No - documented limitation
U13 | url | iitb.ac.in (legit edu) | LOW¦MODERATE | LOW (95) | Pass
U14 | url | youtube.com (legit video) | LOW¦MODERATE | LOW (90) | Pass
U15 | url | linkedin.com (legit social) | LOW | MODERATE (73) | Fail | Allow-listed domain but ML p~0.9 -> damped deficit still 27 points | No - documented limitation
U16 | url | paypa1-login-example.com (digit swap lookalike) | HIGH¦CRITICAL | CRITICAL (5) | Pass
U17 | url | sbi-kyc-update.xyz (kyc phish) | HIGH¦CRITICAL | CRITICAL (3) | Pass
U18 | url | 192.168.4.20 (ip host login) | HIGH¦CRITICAL | CRITICAL (0) | Pass
U19 | url | account-verify.info (brand in subdomain) | HIGH¦CRITICAL | CRITICAL (2) | Pass
U20 | url | kyc-update-hdfc.top (suspicious tld) | HIGH¦CRITICAL | CRITICAL (3) | Pass
U21 | url | evil-site.ru (at-symbol trick) | HIGH¦CRITICAL | CRITICAL (6) | Pass
U22 | url | xn--pple-43d.com (punycode homograph) | HIGH¦CRITICAL | CRITICAL (8) | Pass
U23 | url | bit.ly (shortener (destination unknown)) | MODERATE¦HIGH¦CRITICAL | CRITICAL (2) | Pass
U24 | url | micros0ft-office-support.com (ms lookalike) | HIGH¦CRITICAL | CRITICAL (3) | Pass
U25 | url | amaz0n-orders-refund.icu (amazon lookalike) | HIGH¦CRITICAL | CRITICAL (3) | Pass
U26 | url | netflix-billing-update.support (netflix billing) | HIGH¦CRITICAL | CRITICAL (4) | Pass
U27 | url | verify-session.cfd (apple subdomain trick) | HIGH¦CRITICAL | CRITICAL (3) | Pass
U28 | url | 203.0.113.55 (ip + port + bank) | HIGH¦CRITICAL | CRITICAL (0) | Pass
U29 | url | secure-login-icici.xyz (icici phish) | HIGH¦CRITICAL | CRITICAL (5) | Pass
U30 | url | docs-share.top (google lookalike) | HIGH¦CRITICAL | CRITICAL (3) | Pass
U31 | url | whatsapp-gold-update.com (malware lure) | HIGH¦CRITICAL | CRITICAL (2) | Pass
U32 | url | faceb00k-security-check.com (facebook lookalike) | HIGH¦CRITICAL | CRITICAL (9) | Pass
U33 | url | auth-verify.ga (ms subdomain trick) | HIGH¦CRITICAL | CRITICAL (1) | Pass
U34 | url | free-recharge-jio-offer.online (recharge scam) | HIGH¦CRITICAL | CRITICAL (18) | Pass
U35 | url | pan-aadhaar-link.site (pan aadhaar) | HIGH¦CRITICAL | CRITICAL (4) | Pass
U36 | url | indiapost-redelivery.top (courier) | HIGH¦CRITICAL | CRITICAL (6) | Pass
U37 | url | dhl-parcel-customs-fee.com (customs) | HIGH¦CRITICAL | CRITICAL (22) | Pass
U38 | url | binance-wallet-verify.net (crypto) | HIGH¦CRITICAL | CRITICAL (4) | Pass
U39 | url | steamcommunlty.com (steam lookalike) | HIGH¦CRITICAL | CRITICAL (2) | Pass
U40 | url | g00gle-security-alert.com (google lookalike) | HIGH¦CRITICAL | CRITICAL (3) | Pass
P01 | permission | Calculator: INTERNET | LOW | LOW (100) | Pass
P02 | permission | Calculator: INTERNET, CAMERA, MICROPHONE, CONTACTS, LOCATION_FINE | HIGH¦CRITICAL | HIGH (42) | Pass
P03 | permission | Calculator: INTERNET, MICROPHONE, SMS | MODERATE¦HIGH | MODERATE (66) | Pass
P04 | permission | Flashlight: INTERNET, CAMERA | LOW | LOW (97) | Pass
P05 | permission | Flashlight: INTERNET, CAMERA, SMS, ACCESSIBILITY, OVERLAY | CRITICAL | CRITICAL (38) | Pass
P06 | permission | Maps: INTERNET, LOCATION_FINE, BACKGROUND_LOCATION, NOTIFICATIONS | LOW¦MODERATE | LOW (94) | Pass
P07 | permission | Messaging: INTERNET, CONTACTS, CAMERA, MICROPHONE, SMS, STORAGE | LOW¦MODERATE | LOW (86) | Pass
P08 | permission | Banking: INTERNET, SMS, CAMERA, NOTIFICATIONS | LOW¦MODERATE | LOW (94) | Pass
P09 | permission | Banking: INTERNET, SMS, ACCESSIBILITY, OVERLAY | CRITICAL | HIGH (50) | Fail | By design module tier comes from points (one CRITICAL permission = 25 pts); overall score IS capped CRITICAL via CH_BANKING_TROJAN | Working as designed
P10 | permission | Game: INTERNET, CONTACTS, CALL_LOG, SMS | HIGH¦CRITICAL | HIGH (54) | Pass
P11 | permission | Notes: INTERNET, STORAGE, MICROPHONE | MODERATE¦LOW | LOW (86) | Pass
P12 | permission | Fitness: INTERNET, LOCATION_FINE, BODY_SENSORS, BLUETOOTH | LOW | LOW (95) | Pass
P13 | permission | Music: INTERNET, STORAGE, NOTIFICATIONS, DEVICE_ADMIN | CRITICAL¦HIGH | MODERATE (73) | Fail | By design module tier comes from points; the CRITICAL finding still caps the overall score at 39 (critical floor) | Working as designed
P14 | permission | Shopping: INTERNET, CAMERA, NOTIFICATIONS, LOCATION_COARSE | LOW | LOW (95) | Pass
P15 | permission | Social: INTERNET, CAMERA, MICROPHONE, CONTACTS, LOCATION_FINE, BACKGROUND_LOCATION, SMS | MODERATE¦HIGH | HIGH (54) | Pass
D01 | device | NO: -; NOT SURE: - | LOW | LOW (100) | Pass
D02 | device | NO: mfa;backup; NOT SURE: - | MODERATE | MODERATE (77) | Pass
D03 | device | NO: os_updated;auto_updates;firewall;antivirus;screen_lock;disk_encryption;secure_boot;mfa;backup;bluetooth;public_wifi; NOT SURE: - | CRITICAL | CRITICAL (0) | Pass
D04 | device | NO: -; NOT SURE: os_updated;auto_updates;firewall;antivirus;screen_lock;disk_encryption;secure_boot;mfa;backup;bluetooth;public_wifi | HIGH | HIGH (50) | Pass
D05 | device | NO: backup;auto_updates;disk_encryption; NOT SURE: - | MODERATE¦HIGH | MODERATE (70) | Pass
D06 | device | NO: bluetooth;public_wifi; NOT SURE: - | LOW | LOW (93) | Pass
D07 | device | NO: os_updated;screen_lock;mfa; NOT SURE: - | HIGH¦MODERATE | HIGH (58) | Pass
D08 | device | NO: secure_boot; NOT SURE: mfa | LOW¦MODERATE | LOW (88) | Pass
pytest | all | tests/ (unit + headless UI) | all pass | 73 passed in 11.00s | Pass

## ML Results
Model | Dataset | Accuracy | Precision | Recall | F1 | n_train | n_test | tp | fp | fn | tn
EMAIL - LogisticRegression (selected) | email_dataset.csv (CEAS08-ham + Nazario + Nigerian_Fraud + SpamAssassin-ham) | 0.9929 | 0.9917 | 0.9869 | 0.9893 | 7306 | 1827 | 601 | 5 | 8 | 1213
EMAIL - RandomForest | email_dataset.csv (CEAS08-ham + Nazario + Nigerian_Fraud + SpamAssassin-ham) | 0.9918 | 0.9869 | 0.9885 | 0.9877 | 7306 | 1827 | 602 | 8 | 7 | 1210
URL - RandomForest (selected) | url_dataset.csv (ISCX-URL-2016-benign + PhiUSIIL + PhishTank-2020 + faizann24-malicious-urls) | 0.905 | 0.8928 | 0.9064 | 0.8995 | 67768 | 16942 | 7202 | 865 | 744 | 8131
URL - XGBoost | url_dataset.csv (ISCX-URL-2016-benign + PhiUSIIL + PhishTank-2020 + faizann24-malicious-urls) | 0.9045 | 0.9036 | 0.8915 | 0.8975 | 67768 | 16942 | 7084 | 756 | 862 | 8240
Fusion selection (out-of-fold, training split only)
module | method | rule_weight | precision | recall | f1 | fpr | n
url | linear | 0.3 | 0.8833 | 0.8551 | 0.869 | 0.0998 | 12000
url | linear | 0.4 | 0.9082 | 0.8016 | 0.8516 | 0.0716 | 12000
url | linear | 0.5 | 0.9465 | 0.7076 | 0.8098 | 0.0353 | 12000
url | linear | 0.6 | 0.9782 | 0.5332 | 0.6902 | 0.0105 | 12000
url | max |  | 0.8233 | 0.9242 | 0.8708 | 0.1754 | 12000
url | noisy_or |  | 0.793 | 0.9396 | 0.8601 | 0.2168 | 12000
url | rules_only |  | 0.9539 | 0.0258 | 0.0502 | 0.0011 | 12000
url | ml_only |  | 0.824 | 0.9238 | 0.871 | 0.1744 | 12000
email | linear | 0.3 | 0.993 | 0.9926 | 0.9928 | 0.0035 | 7306
email | linear | 0.4 | 0.9926 | 0.9877 | 0.9901 | 0.0037 | 7306
email | linear | 0.5 | 0.9929 | 0.9819 | 0.9874 | 0.0035 | 7306
email | linear | 0.6 | 0.9892 | 0.8279 | 0.9014 | 0.0045 | 7306
email | max |  | 0.7258 | 0.9963 | 0.8398 | 0.188 | 7306
email | noisy_or |  | 0.6984 | 0.9979 | 0.8217 | 0.2153 | 7306
email | rules_only |  | 0.3833 | 0.2301 | 0.2875 | 0.1849 | 7306
email | ml_only |  | 0.9906 | 0.9959 | 0.9932 | 0.0047 | 7306

## Bugs
Bug ID | Module | Problem | Severity | Owner | Status
BUG-01 | ML-URL | Model trained on PhiUSIIL alone learned 'has a path => phishing' / 'https => legit' (99% test acc, but wikipedia/github deep links scored CRITICAL) | High | Teammate | Fixed - mixed benign deep-link sources, randomised scheme for scheme-less benign URLs
BUG-02 | ML-URL | Trailing '/' on homepages (https://site/) treated as a path - PhiUSIIL artefact made iitb.ac.in/ look like phishing | High | Teammate | Fixed - trailing slash normalised in feature extraction; model retrained
BUG-03 | ML-URL | Random Forest model file was 122 MB (too big to ship) | Medium | Teammate | Fixed - limited depth/trees + joblib compression (13 MB)
BUG-04 | Risk | Score breakdown did not reconcile exactly (module scores rounded to 6 dp) | Medium | Me | Fixed - no rounding inside the engine; reconciliation unit test added
BUG-05 | Password | Samriddhi123 scored CRITICAL: dictionary-word and name+digits findings double counted | Medium | Me | Fixed - word inside Name+digits pattern no longer counted twice
BUG-06 | Fusion | Fixed 60/40 rule/ML blend let a confident ML phishing verdict score only 60 (MODERATE) when rules saw nothing | High | Me | Fixed - fusion method chosen on out-of-fold training data (ml/select_fusion.py)
BUG-07 | Correlation | HIGH-severity chains only capped a module tier, so the overall score stayed MODERATE (scenario study v1: 5/9 dangerous profiles mislabelled) | High | Me | Fixed - HIGH-chain cap at 59 (ablation kept in results)
BUG-08 | UI | Demo buttons set widget state after widget creation (StreamlitAPIException) | Low | Teammate | Fixed - on_click callbacks
BUG-09 | UI | Home page markdown indented inside function rendered as code block | Low | Teammate | Fixed
BUG-10 | Password | Reused-but-strong password still LOW risk (reuse weight 20) | Medium | Me | Fixed - reuse weight 25 (-> MODERATE)
BUG-11 | ML-URL | Legit deep links on non-allow-listed domains (stackoverflow, bbc) still scored HIGH/CRITICAL by ML | Medium | Teammate | Open - shown as UNCERTAIN; needs better benign data
BUG-12 | ML-Email | Short SMS-style legit messages (OTP, delivery) get high phishing probability (dataset shift) | Medium | Teammate | Open - documented; India rules + UNCERTAIN flag mitigate
BUG-13 | Email | UNCERTAIN flag fires on ~40% of URLs/emails because rules have low recall on public corpora | Medium | Me | Open - future work: calibrate rule scores
BUG-14 | Correlation | No chain for reused/weak password + no MFA without an observed lure (P06) or for 'digital arrest' alone (P13) | Low | Me | Open - documented limitation

## Literature
Paper | Year | Problem | Method | Dataset | What we use | Confidence
Ma, Saul, Savage, Voelker - Beyond Blacklists: Learning to Detect Malicious Web Sites from Suspicious URLs (KDD) | 2009 | Malicious URL detection | Lexical + host features, online learning | Own crawl | Lexical URL features idea | Confident
Garera, Provos, Chew, Rubin - A Framework for Detection and Measurement of Phishing Attacks (WORM) | 2007 | Phishing URL detection | URL structure features + logistic regression | Google toolbar data | Obfuscation feature families (@, IP, brand in path) | Confident
Sahingoz, Buber, Demir, Diri - Machine learning based phishing detection from URLs (Expert Systems with Applications) | 2019 | Phishing URL detection | NLP features + RF | Own dataset | Comparison of classical ML on URL features | Confident
Prasad & Chandra - PhiUSIIL: A diverse security profile empowered phishing URL detection framework based on similarity index and incremental learning (Computers & Security) | 2024 | Phishing URL detection | Similarity index + incremental learning | PhiUSIIL (UCI 967) | Dataset used for training | Confident
Mamun, Rathore, Lashkari, Stakhanova, Ghorbani - Detecting Malicious URLs Using Lexical Analysis (NSS) | 2016 | Malicious URL detection | Lexical features | ISCX-URL-2016 | Benign URL list source | Verify venue details
Fette, Sadeh, Tomasic - Learning to Detect Phishing Emails (WWW) | 2007 | Phishing email detection | PILFER: engineered features + RF | SpamAssassin + phishing corpus | Header/URL engineered email features | Confident
Chandrasekaran, Narayanan, Upadhyaya - Phishing email detection based on structural properties (NYS Cyber Security Symposium) | 2006 | Phishing email detection | Structural features + SVM | Own | Structural cues | Verify
Felt, Chin, Hanna, Song, Wagner - Android Permissions Demystified (ACM CCS) | 2011 | Android permission risk | Static analysis of over-privilege | 940 apps | Over-privilege / purpose mismatch idea | Confident
Enck, Ongtang, McDaniel - On Lightweight Mobile Phone Application Certification (ACM CCS) | 2009 | Android permission risk | Kirin: rules over dangerous permission combinations | Android apps | Dangerous-combination rules (e.g. SMS + ...) | Confident
Sarma, Li, Gates, Potharaju, Nita-Rotaru, Molloy - Android Permissions: A Perspective Combining Risks and Benefits (SACMAT) | 2012 | Android permission risk | Category-relative rare-permission risk | Google Play apps | Category baseline for expected permissions | Confident
Lundberg & Lee - A Unified Approach to Interpreting Model Predictions (NeurIPS) | 2017 | Explainability | SHAP values | - | SHAP for URL/email models | Confident
Lundberg et al. - From local explanations to global understanding with explainable AI for trees (Nature Machine Intelligence) | 2020 | Explainability | TreeExplainer | - | TreeExplainer for RF/XGBoost | Confident
Strom et al. - MITRE ATT&CK: Design and Philosophy (MITRE technical report) | 2018 | Threat modelling | ATT&CK knowledge base | - | Technique IDs for findings and chains | Confident
Sheyner, Haines, Jha, Lippmann, Wing - Automated Generation and Analysis of Attack Graphs (IEEE S&P) | 2002 | Attack graphs / risk scoring | Model checking to build attack graphs | Network models | Idea of chaining weaknesses (C1) | Confident
Ou, Govindavajhala, Appel - MulVAL: A Logic-based Network Security Analyzer (USENIX Security) | 2005 | Attack graphs / risk scoring | Datalog rules over vulnerabilities | Network models | Data-driven chain rules (C1) | Confident
Mell, Scarfone, Romanosky - A Complete Guide to the Common Vulnerability Scoring System Version 2.0 (FIRST) | 2007 | Risk scoring | CVSS base/temporal/environmental scoring | - | Severity bands and weighting | Confident
Wachter, Mittelstadt, Russell - Counterfactual Explanations without Opening the Black Box (Harvard JOLT) | 2017 | Counterfactual explanation | Counterfactuals | - | What-If simulator framing (C2) | Confident
Wheeler - zxcvbn: Low-Budget Password Strength Estimation (USENIX Security) | 2016 | Password strength | Pattern-matching entropy estimation | Leaked password sets | Pattern-penalised entropy | Confident
Weir, Aggarwal, Collins, Stern - Testing metrics for password creation policies by attacking large sets of revealed passwords (ACM CCS) | 2010 | Password strength | Shows NIST entropy is a poor metric | RockYou etc. | Why naive entropy is not enough | Confident
Al-Subaiey et al. - Novel Interpretable and Robust Web-based AI Platform for Phishing Email Detection | 2024 | Phishing email detection | Curated multi-corpus dataset + ML | Nazario, SpamAssassin, CEAS, ... | Email corpora mirror | VERIFY author list / venue

## Novelty Evidence
1. Scenario study (C1): plain weighted average vs Threat Correlation Engine
profile | name | baseline_score | baseline_tier | correlated_score | correlated_tier | expected | which_correct | chains | ablation_no_high_cap_tier
P01 | Good hygiene everywhere | 91.5 | LOW | 91.5 | LOW | LOW | both | - | LOW
P02 | Credential-harvest phish, everything else good (problem statement) | 65 | MODERATE | 39 | CRITICAL | CRITICAL | correlated | CH_CRED_HARVEST | CRITICAL
P03 | Demo storyline: weak password + no MFA + KYC phish + nosy calculator | 32.7 | CRITICAL | 25.5 | CRITICAL | CRITICAL | both | CH_ACCOUNT_TAKEOVER;CH_CRED_HARVEST;CH_MOBILE_SURVEILLANCE;CH_INDIA_PAYMENT_SCAM | CRITICAL
P04 | Banking-trojan app, everything else good | 71.1 | MODERATE | 39 | CRITICAL | CRITICAL | correlated | CH_BANKING_TROJAN | CRITICAL
P05 | Common password but MFA on | 62.1 | MODERATE | 62.1 | MODERATE | MODERATE | both | - | MODERATE
P06 | Reused weak password + no MFA, no lure seen | 68.2 | MODERATE | 59 | HIGH | HIGH | correlated | CH_CREDENTIAL_STUFFING | MODERATE
P07 | Stalkerware-like calculator | 77.8 | MODERATE | 59 | HIGH | HIGH | correlated | CH_MOBILE_SURVEILLANCE | MODERATE
P08 | Neglected device (no backup, no updates, no encryption) | 74.8 | MODERATE | 59 | HIGH | HIGH | correlated | CH_UNRECOVERABLE | MODERATE
P09 | UPI collect-request scam message | 66.4 | MODERATE | 59 | HIGH | HIGH | correlated | CH_INDIA_PAYMENT_SCAM | MODERATE
P10 | Partial assessment: strong password + safe URL only | 90.7 | LOW | 90.7 | LOW | LOW | both | - | LOW
P11 | Promotional email, decent password, MFA on | 95.1 | LOW | 95.1 | LOW | LOW | both | - | LOW
P12 | PayPal look-alike login page + reused password + no MFA | 43.3 | HIGH | 33.7 | CRITICAL | CRITICAL | correlated | CH_ACCOUNT_TAKEOVER;CH_CREDENTIAL_STUFFING | CRITICAL
P13 | 'Digital arrest' scam email, otherwise good | 69.6 | MODERATE | 59 | HIGH | HIGH | correlated | CH_COERCION_SCAM | MODERATE
Scenario study (13 profiles, expected tiers assigned a priori) Exact tier agreement: baseline 5/13, correlated 13/13 Dangerous profiles (expected HIGH/CRITICAL): 9 labelled LOW/MODERATE by plain average: 7/9 labelled LOW/MODERATE by correlation engine: 0/9 Ablation (correlation without HIGH-chain cap): exact 8/13, dangerous mislabelled 5/9 Mean absolute tier error: baseline 0.77, correlated 0.00
2. Adversarial URL robustness (detection rate on 300 held-out phishing URLs)
perturbation | n | rules_only | ml_only | hybrid | rules_only_moderate+ | ml_only_moderate+ | hybrid_moderate+
original | 300 | 0.03 | 0.93 | 0.95 | 0.28 | 0.9933 | 0.9867
homoglyph_swap | 300 | 0.0333 | 0.98 | 1 | 0.2967 | 1 | 1
prepend_https | 300 | 0.0167 | 0.8033 | 0.8333 | 0.1433 | 0.91 | 0.9033
url_shortener | 300 | 0 | 1 | 1 | 0 | 1 | 1
long_benign_path | 300 | 0.0733 | 0.47 | 0.5767 | 0.72 | 0.79 | 0.9067
subdomain_padding | 300 | 0.3133 | 1 | 0.98 | 1 | 1 | 1
3. Rule-ML disagreement statistics (held-out test splits)
module | n | disagreement_rate | n_uncertain | rules_correct_when_uncertain | ml_correct_when_uncertain | hybrid_error_rate_uncertain | hybrid_error_rate_certain | share_of_all_hybrid_errors_flagged_uncertain | hybrid_error_rate_overall
url | 3000 | 0.476 | 1428 | 0.152 | 0.8466 | 0.1527 | 0.0681 | 0.6708 | 0.1083
email | 1827 | 0.3853 | 704 | 0.0071 | 0.9929 | 0.0085 | 0.0062 | 0.4615 | 0.0071
4. India-localized test set (28 hand-made messages: 21 scams, 7 legitimate)
configuration | n_scams | n_legit | detection_rate_scams | false_positive_rate_legit
Hybrid WITH India rules (rules + ML) | 21 | 7 | 0.8095 | 0.5714
Hybrid WITHOUT India rules (rules + ML) | 21 | 7 | 0.7619 | 0.5714
Rules only WITH India rules | 21 | 7 | 0.5238 | 0
Rules only WITHOUT India rules | 21 | 7 | 0.381 | 0
ML only (p >= 0.5) | 21 | 7 | 0.619 | 0.5714